## #1. Pre Development Activities
WBS - ProMan AI HRMS Platform - 10-04-2022
Pre Development Tasks
This sheet below shows a ONE-TIME activity. This must be done prior to starting Development.
Sno | Activity |  |  |  | Comments | Man Days
1 | Research & Shortlisting (Technical Feasibility Analysis) |  |  |  | We will look at paid systems and solutions and also explore open soutce/freeware versions. | 10
| 1.1 | AI Platform for Computer Vision (Audio & Video) & Background Verification System |  |  | Systems that do analysis of eye movement, speech and body language in a video stream and/or in images. Systems that heck on a person’s Aadhar database and/or criminal database and/or any other govt. established accredited databases.
Talking to Industry Experts
Discuss Requirements, Suggest Optimizations
Taking Demos
Assess for Speed & Performance
|  |  |  | Assess for Accuracy | Must provide all metrics like height calculation from a picture, face recognition against an uploaded picture, speech and communication analysis, body language/hand posture/ eye movement analysis, confidence detection, EQ detection, fluency. Detect nervousness, familiarity with topic.
|  |  |  | Output Formats and Details Provided | score card exposed, calibration metrics provided
Assess for Security
Study Their SDK/API
Assess Customization
At the 3rd party system's side
Integrations & Connectors we we need to support
Cost Analysis and comarison
Negotiation Disucssions with stake holders
| 1.2 | Shortlisting Final solutions
Pros and Cons analysis
|  |  | Proposing Options, Technical alternatives |  | Not all systems will give everything. We will have to pick on basis of pros and cons.
2 | Technical Specifications Documentation (SRS) |  |  |  | This document is given to UI/UX team and developers Detail out all registration and profile fields, all forms, all data entry input validation rules etc. Detail out data types, admin roles and privileges, types of sms/emails, all types of notifications, all filters and sorting params. | 1.5
| 2.1 | Detail Requirements & Workflow for
Users - Labour Force applying for jobs
Admins - Proman's Hiring Team
| 2.2 | Misc. System requirements like
Notifications, Emails
Background Batch Processing
Support for Whitelabel, Multi Lingual etc.
3 | Architcture Design and Documentation (HLD) |  |  |  | HLD - High Level Design Document High end architecture design covering backend, frontend while accounting for basics like logging, monitoring, seo, performance, scalability, security. FOR PHASE 1 - KEEP OVERALL LOW COMPLEXITY, MORE OUT OF THE BOX APPROACH, STRONG BASE FUNDAMENTALS THAT ALLOW FOR EASY SCALABILITY IN FUTURE | 3
| 3.1 | Functional Mobile App design (iOS and Android Superior mobile app experience) |  |  | Consider latest IT trends, standards and best practices.
With whitelabel support, App Skinning, Branding changes
| 3.2 | Database Design |  |  | Schema design for web and mobile
| 3.3 | Integrations and Connectors |  |  | Core Web server with batch processes, services layer with API, 3rd party integrations
|  |  | Computer Vision system Integration for Speech and Audio analysis |  | Account for Rate limiting, Throttling, Exception Handling etc.
|  |  | Background system and verification |  | Json response format to be defined for response handling
SMS gateway
Email handling
| 3.4 | Probable Services Layer (Web Services)
Authentication, Authorization
Start listing initial basic set of services/api's which we will need to make
Basic Interface definition
Account for Whitelabel and Branding Elements
| 3.5 | Business layer logic and Components - LLD
Algorithms & Scoring for Weights
Permissions Layer & ACL's
| 3.6 | Core Support Modules
|  |  | Sync |  | b/w web server and Mobile , b/w mobile devices of same user
Real time notifications
i18n Internationalization
| 3.7 | Performance Considerations |  |  | Response time optimization
Frontend and Page Load
Backend - server and database
Video Processing & Rendering
| 3.8 | Security |  |  | SSL and https, Encrypted Storage
Encryption and Privacy
| 3.9 | Scalability & Cloud Deployment Architcture |  |  | - Planning the deployment architecture for QA, Pre-prod/Staging and Prod. - Set the deployment report and document/params to be monitored etc.
Horizontal and Vertical scaling
|  |  | Hardware Procurement Optimization |  | For AWS accounting for load balancing
| Total Efforts |  |  |  | Man Days | 14.5

## #2. Design, Develop & Test
WBS - ProMan AI HRMS Platform - 10-04-2022
[5 empty] | CODING EFFORTS |  |  |  | DESIGN EFFORTS
Sno | Activity |  |  |  | Man Days (Coding) | Man Days (Implementing API - accounts for crud with DB) | Man Days coding web app using API) | Man Days (Coding Mobile App using API) | Man Days (UI design) | Man Days (Slicing) | Comments
# 1. UX Wireframing & UI Design
1 | Storyboarding & Wireframing (All Screens)
| 1.1 | Android Mobile App - Portrait Optimized (For Mobile Phones Only) | [8 empty] | Tablet optimization for later
Layout & Navigation
App Icon/ Splash Page
OTP Based Authentication & Login
Profile screen
See List of Locations/Sites
Change Language
Access Job Description
Application Form (Phased Wise)
|  |  |  | Enter Basic Details | [6 empty] | Name, DOB, Permanent Address
Upload Pic
Upload Document
|  |  |  | Keyboard Based answers | [6 empty] | Cap on total characters allowed. 2-3 such questions
Multiple Choice, Radio check questions
3-4 Video record and Upload questions
Reading chart and Record
|  |  | Edit, Submit Final Form | [7 empty] | One time submission Only. Edit not included in phase 1
User messages
|  |  |  | Confirmation | [6 empty] | on final submit, on successful login etc
Notices
Multiple Attempts
use ack messages
error messages
Status bar for completion
|  |  | Status Page | [7 empty] | see status of application, acceptance /rejection status
|  |  | Notifications and Email Design | [7 empty] | only for super admins
Privacy Page
Basic Mobile app Settings
Permissions - access to camera, microphone
Feedback Engine
| 1.2 | Web Admin Panel dashboard
Admin Login, forgot pwd
Upload excel file with Numbers
Send invites to apply for a particular site, general
See submitted applications
View video answers
View all answers (writte, multiple choice)
View verification status
View score, metrics like height
Download report summarizing all info above for candidate
Filter by date, site, status
Update status - accepted/rejected
Report pdf design
2 | Responsive UI Design
Font, Color Family finalization
Master Template Created
Finalization of all screens
# 1. BACKEND (PROMAN SERVER)
1 | Application server - Code setup, configuration, Install
2 | Relational DB - DB Settings & Setup
3 | Connector for Computer Vision System |  |  |  | 30
Session Mgmt. (start, stop)
Recording, tagging with candidate name etc. & encryption
Metering and monitoring session quality
Notifications
Enable features like compression
4 | Connector for Background verification System
5 | Backend Implementation for Admin User Types and ACL's (2 user roles) | [9 empty] | 2 roles to be supported
6 | Backend Logic for various modules
Notifications
|  | weighted algorithm | [8 empty] | basic scoring algorithm in phase 1
7 | Background Processes/Cron Jobs
Video storing
Sending video and Fetching results
Report generation
auto expiry of video recordings
8 | i18n (Internationalization support) | [9 empty] | Launching in english and hindi both. Translations to come from client.
Launch in Hindi in phase 1
9 | White Label support | [9 empty] | Only basic support to be added. It wont be released as a whitelabeled app in phase 1
#3. Super Admin Panel - This is also a WEB App used by Product Owners Only
Efforts below include man hours to Make api call TO WEB SERVER, get response, integrate in view.
1 | Login and Accounts
Login as Admin & Pwd recovery
Email account activation forgot pwd, logout, reset pwd
2 | View Submitted Applications
View all answers
See/Hear Video/Audio
See Candidate's metrics
Height
Profile Picture match
|  |  | Bgd. Verification | [7 empty] | wont process full application if bgd verification fails.
Communication Skills, Reading/Speaking skills - speech fluency, look for gaps, stuttering, fluency, clarity of voice
Speech modulation - detect confidence
speech to text - detect keywords and gramatical errors
Body language recognition: Duration of eye contact during the video answer
Level of hand movement - Posture recognition to gauge confidence and nervousness, familiarity with the topic
Understand EQ of the candidate - through stress analysis in voice and speech.
|  | Score generated by our weighted algorithm | [8 empty] | Score to be generated out of 100. Each of the aspects like communication, body language, EQ, content, etc to be given a %. E.g. communication is 20%, EQ is 30%, eye contact and hand posture in body lang is 50% and so on. We will do a simple avg weighted algorithm to calculate the final score which will be out of 100.
3 | Filter Applications
By date, By Site, By Location
4 | Update Application Status
Mark as selected, rejected
5 | Access and Download Report per application
6 | Upload excel file with numbers
7 | Send invites for registration and application
Location based broadcasting
8 | QR code/Link based Invitations
#4. User Facing Mobile App
These are efforts for coding - Make api call, get response, integrate in view.
1 | User Registration (Expert by Default)
OTP based Login
OTP phone / email verification
2 | Candidate Profile
Name, DOB, Address, Picture, Document
Location
Languages
3 | Profile view
4 | List of Sites
5 | GeoTagging Support (for site location, user's location)
6 | Start Application
|  | Timer alert on video | [8 empty] | wont get to videos if pic and bgd verification fails.
Long scroll
7 | Save/Edit application | [9 empty] | not in phase 1
8 | Submit
9 | Status Page
10 | Account Settings
Select language
Select settings for reminders/notifications?
11 | Misc.
|  | Toast messages | [8 empty] | needed in both languages
12 | Notifications
Application pending, submitted
13 | Security
API based authentication - session / token
SSL Integration for user facing Web App
Custom Error Pages
Form UI validations
XSS, CSRF
14 | Layouts for mobile
Portrait
15 | Access saved application which was submitted?
Total development Effort
OTHER INTEGRATIONS AND TASKS NEEDED
1 | Interaction with other 3rd party providers for tech support, integration, sdk queries etc.
Quality Assurance
|  |  | Manual QA efforts | [7 empty] | Includes testing and debugging Regression testing Involves testing of: - super admin panel - user facing web app - iOS and Android app across screen sizes
|  |  | Testing with Data | [7 empty] | 1. setup dummy DB and dummy data 2. Add dummy builds 3. Create dummy content 4. Organize demos
Tech Lead Time in milestones
Tech Lead
Machines and EED
|  |  | DEVOPS & SYSADMIN Create and Setup QA, Pre-Prod, Prod environments | [7 empty] | // Setup machines, make and enable monitoring, logs dashboard 1. Setting up the deployment stack as per document 2. Deploying latest versions of code on QA, pre-prod, prod environments 3. Creating and managing QA and pre-prod environments 4. Creating and setting up production environment 5. Setting up crons, daemon processes, setting proxies etc.
App Interface, Final Publication
Publication to Google store
Project & Delivery Management
|  |  | PM efforts | [7 empty] | Client standup calls, Regular developer meetings, resource and time management, resolving all technical roadblocks Version control
|  |  |  | UAT | [6 empty] | Addressing client's concerns, mapping tickets to CR's vs. bugs, filing bugs in PM tool, Updating Reports
Release Notes

## #3. Assumptions
NOTES
This WBS is a snapshot of the technical quantum of work required to make Phase 1 of the platform.
This WBS does not capture Phase 2 features
The features included here are on basis of all discussions with Ankur till date on April 13th 2022.
This is a fixed cost milestone based project where we will give multiple releases.
- We will aim to do an Android store launch only in India and iOS is not included. - AWS account will be needed from client to run QA, staging and prod servers. - Costs for 3rd party systems to be negotiated directly with 3rd parties and payments to be made directly to them.
FOR PURPOSES OF THESE ESTIMATES, WE HAVE ASSUMED THE FOLLOWING:
1. Basic Support for whitelabel will be added in backend and in database schema, however in Phase 1 this will be launched as a single branded app (maybe ProMan branded or otherwise) and no separate skinning / additional branding will be done. For each new white-labeled version to be released, that is separate effort which can be discussed post Phase 1 2. Support will be added to support multi languages but first launch will be in English and hindi only. Client to provide the hindi translations and we to feed them into system. 3. All the metrics we need for applicant like height, profile pic match and all parameters like bgd. verification, Aadhar entity match, confidence score, speech analysis, detection of fluency, nervousness, confidence, EQ, body language etc are to be provided by 3rd party system. 4. These estimates do not assume writing of any data models or ML algos by Atlogys. We must depend on existing sdk’s/Api’s and 3rd party systems that do video and speech analysis to determine all values as required above. 5. This WBS also assumes that we will be integrating with one system that does audio and speech analysis and one more system for background verification. If we are required to integrate with more than two outside ( 3rd party ) systems for video/pic/speech analysis, then the man days of development will need to be altered affecting the total price and timeline. 6. The scoring algo will do a weighted average. The details have been added in wbs and we will provide for that in Phase 1. Scoring will be out of 100%. 7. No separate rating or review feature is being provided at the moment. 8. The scoring also cant be edited or customized for different users. The calibration metrics will be pre-set. 9. No search feature has been discussed and/or provided for. We will allow admins to filter applications coming in by date of submission and site.
10. No invite to others is supported. 11. Basic mobile settings needed by all apps are being provided for like permission access, language, privacy settings. 12. Feature to generate clubbed report for more than 1 person is not included in phase 1. 13. Any features not listed in this WBS OR not discussed till date (not referenced in specs sheet received from client) is Not included in this WBS 14. This will account for a portrait optimized mobile app only, Not tablets app. 15. The application form for applying will Not have surveys, polls, graphical and animated questions in phase 1. 16. There will be no feature of save answers and resume application later in phase 1. 17. Only 2 user roles are being provided for in the system to begin with (admin and applicant) 18. To begin with in phase 1, we will need to encode (feed) the list of sites along with their locations. There will be no feature to add/edit sites from the SA panel in phase 1. Similarly all admin accounts will be pre-created. In phase 2 we can add feature to allow admins to create more admin users form the backend. 19. Things like monitoring the quality of video/audio being uploaded by user in application is not included in phase 1. 20. Sync between multiple devices of users is not being supported
21. We will not store the videos on 3rd party systems or on users mobile devices. 22. Report is a simple collation of metrics received from 3rd party. There is no separate report generation logic being accounted for in phase 1. 23. Social integrations for whats app, fb, Li, g+ etc have not been discussed and not included at the moment. 24. Geotagging restricted to user’s location and site’s location. 25. There is no concept of sign Up. Applicants will get a qr code or sms link using which they will access app and do an OTP based login to start application. 26. The application will not be complicated with RTE and auto fills or auto completes. 27. Job descriptions will be pre-fed into the system. In phase 2 we can add support to create dynamic jobs on the dashboard. 28. No feature to customize questions in phase 1.
29. For both connectors we have assumed max 20-30 man days of work for integrations and customizations required for that in our backend. 30. Below are certain good to haves which are not included in phase 1 a. Certain login like how many times a candidate can apply per site, can the person apply for more than one site, how many applications can they submit over a time period – these have not been discussed and hence any such logic is not included in the wbs at the moment. b. Profile completeness widget or application completeness widget c. Customer support, Ticketing d. Social integrations e. Friend invite f. Implementing Abuse module g. In app notifications h. User moderation (activate, de-activate users) i. Business and operational analytics (Like # of users on system 7 day active, # of applications submitted, # of accepted, # of rejected, # of sessions, total downloads j. Social login with whats app, G+. fb k. Profile pre-filled from social media profiles l. System level analysics, user level analytics m. Blocked and blacklisted user states 30. OS versions to be supported are versions 19 to 30
Overall, we have considered Phase 1 to be of low complexity but have done detailed holistic thinking of all features that will go in phase 1. More of an out of the box approach when it comes to solr.
The focus for Phase 1 will be more on fundamental architecture so the app may scale well in the future.
Make the mobile app in phase 1 with a superior user experience that goes live on app stores
Assuming responsive UI will be provided for mobile screens as needed by PhoneGap
Server Monitoring post production launch like peak traffic etc is not included.
AWS costs not included in this proposal.